## Gantt Chart
ISMS PROJECT IMPLEMENTATION
PROJECT TITLE |  | NUSUSI SACCO ISMS PROJECT IMPLEMENTATION |  |  |  |  | COMPANY NAME | [6 empty] | NUSUSI SACCO
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | [6 empty] | 2026-01-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Initiate ISMS Project | Project Manager | 2026-01-12 | 2026-01-12 | 0 | 100% | bar: WEEK 1 F to WEEK 2 T
1.2 | Project Charter | Project Manager | 2026-01-12 | 2026-01-13 | 1 | 100% | bar: WEEK 2 W
1.2 | Conduct Management Awareness Session | ISO Consultant | 2026-01-13 | 2026-01-13 | 0 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Secure Management Commitment through Management Approval Forms | Project Manager | 2026-01-14 | 2026-01-15 | 1 | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Understand Organization Context | ISO Consultant | 2026-01-15 | 2026-01-18 | 3 | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 | Understand Stakeholder Needs | ISO Consultant | 2026-01-15 | 2026-01-18 | 3 | 60% | bar: WEEK 3 T to WEEK 3 R
1.5 | Define Project Scope | Project Manager, ISO Consultant | 2026-01-19 | 2026-01-22 | 3 | 50% | bar: WEEK 3 F
2 | Project Execution
2.1 | Conduct Gap Analysis & Readiness Assessment | ISO Consultant | 2018-03-24 | 2018-03-28 | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 | Develop Risk Management Process | ISO Consultant | 2018-03-29 | 2018-04-02 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | Conduct Risk Assessment | Project Manager, ISO Consultant |  |  | 0 | 0%
2.4 | Develop Risk Treatment Plan | ISO Consultant
2.5 | Develop Statement of Applicability | ISO Consultant |  |  | 0 | 0%
3 | Project Implementation
3.1 | Develop Information Security Policies | Project Manager, ISO Consultant |  |  | 0 | 0%
3.2 | Develop Supporting Procedures/ Work Instructions | Project Manager, ISO Consultant |  |  | 0 | 0%
3.3 | Implement Selected Controls | IT Department |  |  | 0 | 0%
3.4 | Document Set - Awareness Programs, IRP, BIA | Project Manager, ISO Consultant, IT Department |  |  | 0 | 0%
3.3 | Conduct Training and Awareness | HR, IT, ISO Consultant |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Monitor & Measure ISMS Performance | IT Department, ISO Consultant |  |  | 0 | 0%
4.2 | Perform Internal Audit | Internal Audit Team |  |  | 0 | 0%
4.3 | Conduct Management Review Meetings | Management |  |  | 0 | 0%
4.4 | Treat Non-Conformities | Malik M |  |  | 0 | 0%
4.5 | Implement Continuous Improvement | Project Manager, ISO Consultant
4.6 | Prepare for Certication Audit